## Sheet1
Ref. no. | Phase | Task | Optimistic effort | Pessimistic effort | Most likely effort | Expected effort
Module: Overall project
1 | Project initiation | overall initiation activites | 1 | 2 | 2 | 1.83
16 | Requirements analysis | Plan interviews | 2 | 4 | 3 | 3
17 | Requirements analysis | Conduct interviews with subject matter experts | 5 | 9 | 6 | 6.33
18 | Requirements analysis | Consolidate interview findings | 3 | 4 | 3.5 | 3.5
19 | Requirements analysis | Document requirements | 4 | 6 | 5 | 5
20 | Requirements analysis | Review requirements document | 1 | 1.5 | 1 | 1.08
21 | Requirements analysis | Customer approval | 2 | 4 | 3 | 3
26 | SRS | Prepare SRS document | 3 | 5 | 4 | 4
27 | SRS | Review of SRS document | 2 | 4 | 2.5 | 2.67
28 | SRS | Coordinate and obtain customer approval | 5 | 8 | 6 | 6.17
2 | Postdelivery | Install | 0.5 | 1 | 0.75 | 0.75
3 | Postdelivery | On-site support | 2 | 3 | 2 | 2.17
11 | Project closure | Document best practices | 2 | 4 | 3 | 3
12 | Project closure | Document bad experiences | 1 | 2 | 1.5 | 1.5
13 | Project closure | Archive project records | 3 | 5 | 4 | 4
14 | Project closure | Release resources | 1 | 1.5 | 1.25 | 1.25
15 | Project closure | Conduct project postmortem | 1 | 1.5 | 1.25 | 1.25
5 | Documentation | Prepare user guide | 2 | 3 | 2.5 | 2.5
6 | Documentation | Prepare operations manual | 1 | 2 | 1.5 | 1.5
7 | Documentation | Review documentation | 1 | 2 | 1.5 | 1.5
53 | Test planning | Test strategy | 1 | 2 | 1.5 | 1.5
54 | Test planning | Develop test plans | 4 | 8 | 5 | 5.33
55 | Test planning | Review test plans | 2 | 4 | 3 | 3
56 | System testing | Set up test environment | 1 | 3 | 1 | 1.33
57 | System testing | Conduct system testing | 3 | 6 | 4 | 4.17
58 | System testing | Fix defects | 1 | 1.5 | 1.25 | 1.25
59 | System testing | Conduct load testing | 3 | 5 | 4 | 4
60 | System testing | Fix defects unearthed in load testing | 3 | 6 | 5 | 4.83
61 | System testing | Conduct functional testing | 2 | 3 | 2.5 | 2.5
62 | System testing | Fix defects found in functional testing | 1 | 3 | 2 | 2
63 | System testing | Review test results | 1 | 2 | 2 | 1.83
11 | User acceptance testing | Prepare test plan | 3 | 5 | 4 | 4
12 | User acceptance testing | Review test plan | 1 | 2 | 1.5 | 1.5
13 | User acceptance testing | Customer approval | 5 | 8 | 6 | 6.17
14 | User acceptance testing | Set up testing environment | 1 | 2 | 1.5 | 1.5
15 | User acceptance testing | Conduct user acceptance testing | 4 | 6 | 5 | 5
16 | User acceptance testing | Obtain sign-off | 1 | 2 | 1.5 | 1.5
8 | User training | Prepare training material | 4 | 8 | 5 | 5.33
9 | User training | Prepare course material | 6 | 10 | 7 | 7.33
10 | User training | Conduct user training | 3 | 4 | 3 | 3.17
11 | Module 1 | task1 | 5 | 20 | 10 | 10.83
[5 empty] | Person days | 134.07
[5 empty] | Person month | 7.3